## Table Tracker (hidden)
Schema Layer | Table Name | Details | Schema Finalized | Source Available | Source Link | Data Populated | Code | Data Cleaned / QC | Blockers / Remarks
Layer 1 - Independent
Layer 1 - Independent | events | Master registry of all event types that can be logged in the system. | In Review | No |  | No |  | Not Started | to discuss list of events
| pdi_types | Lookup table defining the context types for Pre-Delivery Inspections. | In Review | No |  | No |  | N/A | to discuss list of pdis
| permissions | RBAC permission profile table with boolean flags per system action. | In Review | No |  | No |  | Not Started | what permssions to create?
| roles | User role definitions linked to permission profiles. | In Review | No |  | No |  | Not Started | what roles to create?
| users | LetzRyd internal staff accounts and login credentials. | In Review | Partial | Walk In Form | Yes | LetzRyd_QC_Report_1_Code | Not Started
| cities | City master table. All city-specific entities reference this table. | In Review | Yes | Onboarding | Yes | LetzRyd_QC_Report_1_Code | Not Started
| hubs_and_parking | Physical location master for LetzRyd hubs and parking lots. | In Review |  | Copy Adjustment-Form (Pan India) ,Copy Maintenance IN & Out _V2 | Yes | LetzRyd_hubs_and_parking_script | Not Started
| rental_plans | Rental and revenue-share plan definitions per city. | In Review |  | Copy Adjustment-Form (Pan India),Adjustment Response | Yes | LetzRyd_rental_plans_script | Not Started
| partners | Fleet partner master — individuals and operators. | In Review |  | Onboarding form_V2 ,Form responses 1 (Adj) | Yes | LetzRyd_partners_script | Not Started
| drivers | Core driver identity and banking master. | In Review | Yes | Onboarding / Walk In Form | Yes | LetzRyd_QC_Report_1_Code | Not Started
| driver_documents | Document vault for all driver KYC documents with version history. | In Review | Yes | Onboarding form_V2 | Yes | LetzRyd_QC_Report_1_Code | Not Started | DL expiry filled with DL No at many places
| vehicles | Vehicle master registry for the entire LetzRyd fleet. | In Review | Yes | Vehicle Status List_V3 , Copy Pan India Master Sheet | Yes | LetzRyd_vehicles_script | Not Started
| vehicle_compliance | Compliance certificate lifecycle per vehicle — PUC, Fitness, Insurance, Permit. | In Review | No |  | No |  | Not Started
| workshops | Workshop and garage master with type and capability details. | In Review | Yes | Copy Maintenance IN & Out _V2 , Invoice Responses , Daily Vehicle Status, Maintenance Inwards | Yes | LetzRyd_workshops_script | Not Started | workshop gst/address etc missing
| walkin_leads | Log of walk-in prospects at LetzRyd hubs. | In Review | Yes | Walk In Form | Yes | LetzRyd_QC_Report_1_Code | Not Started | used Walk in Form for this
| driver_onboarding | Driver onboarding workflow — BGV, training, kit issuance tracking. | In Review | Yes | Onboarding form_V2 | Yes | LetzRyd_QC_Report_1_Code | Not Started
| gps_log | High-frequency GPS ping log — lat/long, speed, heading, cumulative distance. | In Review | Yes | Copy GPS | Yes | LetzRyd_gps_log_script | Not Started
| challan_logs | Traffic violation challan records per vehicle with driver attribution. | In Review | Yes | Traffic Challan details | Yes | LetzRyd_challan_logs_script | Not Started
Layer 2 - Dependent
Layer 2 - Dependent | data_imports | Audit log for all platform file import batches. | In Review | N/A |  | No |  | Not Started
| user_roles | Many-to-many bridge between users and roles for multi-role support. | In Review | N/A |  | No |  | Not Started
| vehicle_assignments | Every vehicle movement event — Allocation, Drop-off, Swap, Maintenance. | In Review | Partial | Copy Pan India Master Sheet.xlsx (Sheets: Vehicle Allocation, Drop off History) OR Copy Blr_Payment Summary [ Internal ].xlsx (Sheet: Allocation) | No | LetzRyd_vehicle_assignments_script | Not Started
| pdi_logs | Pre-Delivery Inspection records linked to assignment events. | In Review | No | Copy of Maintenance IN & Out _V2.xlsx (Sheet: Vehicle Audit Form) | No |  | Not Started
| maintenance_pipeline | Parent record for each maintenance job from inward to outward. | In Review | Yes | Copy of Maintenance IN & Out _V2.xlsx (Sheets: Master Sheet IN & Out, Maintenance Inwards) | Yes | LetzRyd_maintenance_invoices_script | Not Started
| maintenance_logs | Step-by-step lifecycle log for each maintenance job stage. | In Review | Yes | Copy of Maintenance IN & Out _V2.xlsx (Sheets: Maintenance Inwards, Daily Vehicle Status V2) | Yes | LetzRyd_maintenance_logs_script | Not Started
| maintenance_invoices | Workshop invoices with full payment tracking. | In Review | Yes | Copy Maintenance IN & Out _V2 , Maintenance Inwards, Invoice Responses | Yes | LetzRyd_maintenance_invoices_script | Not Started
| accidents | Accident records — fault, damage estimate, insurance claim status. | In Review | Yes | Copy Maintenace IN & OUT_V2 | Yes | LetzRyd_accidents_script | Not Started | Copy Maintenance IN & Out _V2 : Tab - Accident Report (Fully Empty)
| insurance_claims | Full insurance claim lifecycle linked to accidents. | In Review | Yes | Maintenance IN & Out _V2.xlsx (Sheet: Insurance) | Yes |  | Not Started
| media_attachments | Polymorphic file and photo store for any entity type. | In Review | No |  | No |  | Not Started
| tickets | Driver and partner support ticket system. | In Review | No |  | No |  | Not Started
| trips | Individual trip records imported from Ola, Uber, and Rapido. | In Review | Yes | Ola , Uber , Rapido | Yes | LetzRyd - trips Table ETL Script | Not Started
| adjustment_logs | Manual financial adjustments with two-stage Ops + Finance approval. | In Review | Yes | Copy Adjustment-Form (Pan India).xlsx (Sheets: Form responses 1, Adjustment Response) | Yes | LetzRyd_adjustment_logs_script | Not Started
Layer 3 - Ledger
Layer 3 - Ledger | driver_ledger | Double-entry ledger for all driver-level financial events. | In Review | Derived |  | No |  | Not Started
| vehicle_ledger | Double-entry ledger for all vehicle-level financial events. | In Review | Derived |  | No |  | Not Started
| financial_ledger | Master financial ledger — all transactions across entities. | In Review | Derived |  | No |  | Not Started
Layer 4 - Hisaab & Financial
Layer 4 - Hisaab & Financial | hisaab_master | Weekly settlement cycle master — one record per city per week. | In Review | N/A |  | No |  | Not Started
| hisaab | Weekly settlement detail for Driver, Vehicle, or Partner. | In Review | Partial |  | No |  | Not Started
Layer 5 - Analytics & Views
Layer 5 - Analytics & Views | daily_driver_ledger | Daily driver performance summary — trips, earnings, rent, payout. | In Review | Derived |  | No |  | Not Started
| challan_driver_view | Resolved driver-to-challan mapping via assignment date lookup. | In Review | Derived |  | No |  | Not Started
| daily_vehicle_ledger | Daily vehicle KPI snapshot — km, revenue, maintenance, daily P&L. | In Review | Derived |  | No |  | Not Started
| daily_partner_ledger | Daily partner financial summary — revenue, expenses, balance. | In Review | Derived |  | No |  | Not Started
| fleet_performance_daily | City-level fleet KPI snapshot — active vehicles, trips, revenue. | In Review | Derived |  | No |  | Not Started
| maintenance_summary | Monthly maintenance summary per vehicle — cost, downtime, frequency. | In Review | Derived |  | No |  | Not Started

## Table Tracker Updated
Schema Layer | Table Name | Details | Schema Finalized | Source Available | Source/Link | Data Populated | Code | Data Cleaned / QC | Blockers / Remarks
Layer 1 — Independent
Layer 1 — Independent | events | Master registry of all event types that can be logged in the system. | In Review | No | Assumed Data | Partial
| pdi_types | Lookup table defining the context types for Pre-Delivery Inspections. | In Review | No | Not Available | No |  |  | Please provide the complete list of inspection/PDI types.
| permissions | RBAC permission profile table with boolean flags per system action. | In Review | Yes | LetzRyd_RBAC_Framework | Yes | LetzRyd_permissions_script |  | Please provide the list of permissions and access controls.
| roles | User role definitions linked to permission profiles. | In Review | Yes | LetzRyd_RBAC_Framework | Yes | LetzRyd_roles_etl_script |  | Please provide the list of roles, access levels, and role-to-permission mapping.
| users | LetzRyd internal staff accounts. | In Review | Partial | Filled using data from the Executive field in the Walk-in form. | Partial | LetzRyd_QC_Report_1_Code |  | Please provide the list of users (employees), departments, roles, and access mappings.
| cities | City master table. | In Review | Yes | Filled using the City field from the Onboarding Form. | Yes | LetzRyd_QC_Report_1_Code |  | Bengaluru, Hyderabad, and Mumbai populated.
| hubs_and_parking | Physical location master for hubs and parking lots. | In Review | No | Assumed Placeholder Data | Partial | LetzRyd_hubs_and_parking_script |  | Placeholder hub and parking records populated. Actual locations, addresses, pincodes, and capacities required.
| rental_plans | Rental and revenue-share plan definitions per city. | In Review | No | Assumed Placeholder Data | Partial | LetzRyd_rental_plans_script |  | Placeholder rental plans populated. Actual pricing, plan definitions, approval workflows, and versioning rules required.
| car_age_rental_discount_master | Master table defining rental discounts by vehicle make and age. | In Review | No | Not Available | No |  |  | Please provide vehicle age discount rules, age slabs, and discount values.
| partners | Fleet partner master table. | In Review | Partial | Which source to use? (Partners are visible in Hisaab) — No dedicated partner tab available. | Partial | LetzRyd - Partners ETL |  | No structured partner source available. Need official partner master list.
| drivers | Core driver identity and banking master. | In Review | Yes | Onboarding / Walk In Form | Yes | LetzRyd_QC_Report_1_Code |  | Data quality issues in KYC and identity fields (DL expiry parsing errors, invalid UPI/IFSC/PAN/Aadhaar formats, duplicate DL numbers).
| driver_documents | Document vault for all driver KYC documents. | In Review | Yes | Onboarding Form | Yes | LetzRyd_QC_Report_1_Code |  | Many driver records have missing document links.
| vehicles | Vehicle master registry for the entire fleet. | In Review | Partial | Vehicle Status | Partial | LetzRyd_vehicles_script |  | Need registration date, fuel type, date the car was added to the system, RC details, insurance details, and other related vehicle information.
| vehicle_compliance | Compliance certificate tracking per vehicle. | In Review | No | Not Available | No |  |  | Please provide compliance data and document sources.
| workshops | Workshop and garage master table. | In Review | Partial | Maintenance IN/OUT | Yes | LetzRyd_workshops_script |  | Data not cleaned; no standard naming convention and duplicate workshop records present (only workshop name and city available). - Have to Extract data from Vehicle Maintenance
| walkin_leads | Log of walk-in prospects at LetzRyd hubs. | In Review | Yes | Walk In Form | Yes | LetzRyd_QC_Report_1_Code |  | Data quality issues only; most of the data is available, requires cleaning and standardization.
| driver_onboarding | Driver onboarding workflow tracking. | In Review | Yes | Onboarding form_V2 | Yes | LetzRyd_QC_Report_1_Code |  | Data quality issues only; most of the data is available, requires cleaning and standardization.
| gps_log | High-frequency GPS ping data per vehicle. | In Review | Yes | GPS Sheet | Yes | LetzRyd_gps_log_script
| challan_logs | Traffic violation challan records. | In Review | No | Challan Sheet - MUM Hisaab | No | LetzRyd_challan_logs_script |  | Need to finalize the challan API to pull this data
Layer 2 — Dependent
Layer 2 — Dependent | jama_logs | Log for JAMA (vehicle surrender) events, linked to allocation form. | In Review | No | Not Available | No
| vehicle_states | Live state tracker for every vehicle (Available, Jama, Maintenance, RFD). | In Review | Derived |  | No |  |  | This table will track current state of the vehicle ( RFD, In Maintenance etc)
| car_rental_discount | Custom discount overrides applied to specific vehicles. | In Review | No | Not Available | No |  |  | Any custom vehicle-level discounts, if provided, can be tracked here. (Optional Table)
| driver_rental_discount | Custom discount overrides applied to specific drivers. | In Review | No | Not Available | No |  |  | Any custom driver-level discounts, if provided, can be tracked here. (Optional Table)
| data_imports | Audit log for all platform file | In Review | Derived |  | Partial |  |  | For data uploads from files, APIs, etc., this will store when and what data was uploaded.
| user_roles | Many-to-many bridge between users and roles. | In Review | No | Not Available | No |  |  | This will be created once the Users and Roles tables are populated.
| vehicle_assignments | Every vehicle movement event: Allocation, Drop-off, Swap, Parked, Maintenance. | In Review | Partial | Copy Vehicle Status List_V3 :Tab: Work Sheet 2 | Partial | LetzRyd - vehicle_assignments Table ETL Script |  | Car swap, parked, etc. data is not available. Data is available only for drop-off, allocation, and maintenance. Please provide sources connected to these events.
| pdi_logs | Pre-Delivery Inspection records linked to assignments. | In Review | Partial | Copy of Pan India Master Sheet: Vehicle Force Recovery, Vehicle Allocation | No |  |  | Will be filled once we have a complete list of all PDI checkpoints. Currently, we have data only for some checkpoints such as allocation, force recovery.
| maintenance_pipeline | Parent record for each maintenance job. | In Review | Yes | Copy Maintenance IN & Out _V2 | Yes | LetzRyd_maintenance_logs_script
| maintenance_logs | Step-by-step lifecycle log for each maintenance pipeline. | In Review | Yes | Copy Maintenance IN & Out _V2 | Yes | LetzRyd_maintenance_logs_script
| maintenance_invoices | Workshop invoices with full itemised cost breakdown. | In Review | Yes | Copy Maintenance IN & Out _V2 | Yes | LetzRyd_maintenance_invoices_script
| accidents | Accident event records linked to vehicles and drivers. | In Review | No | Need Accident data | Yes | LetzRyd_accidents_script |  | Filled using maintenance data. Accident report data is not accessible.
| insurance_claims | Insurance claims raised for accident or damage events. | In Review | Partial | Copy Maintenance IN & Out _V2 : Tab: Maintenance Inwards | Partial | LetzRyd - Insurance Claims ETL
| media_attachments | Generic media/document attachments for any entity. | In Review | No | Optional Table | No |  |  | Created a separate media attachment table, which can be used for accidents, maintenance, documents, etc. It can also be used for any other documents where no dedicated table exists (optional table).
| tickets | Internal support/ops ticket system. | In Review | No | Optional Table | No |  |  | Please provide tickets/queries raised by drivers/partners, etc., if required.
Layer 3 — Ledger
Layer 3 — Ledger | trips | Individual trip records imported from platform data. | In Review | Yes | RAPIDO — letzryd(45) , OLA — Samvreeddhi Mobility Private Limited , UBER — 20260323-20260330-trip_activity | Yes | LetzRyd - trips Table ETL Script |  | Please let us know if there are any specific columns from particular platforms that need to be stored.
| adjustment_logs | Manual financial adjustment entries with dual approval. | In Review | Partial | Copy Adjustment-Form (Pan India) | Yes | LetzRyd - Adjustment Logs ETL
| driver_ledger | Event-driven ledger for driver-level events. | In Review | Partial | Derived | Yes
| vehicle_ledger | Event-driven ledger for vehicle-level events. | In Review | No | Derived | No
| financial_ledger | Master financial ledger covering all monetary transactions. | In Review | No | Derived | No
Layer 4 — Hisaab and Financial
Layer 4 — Hisaab and Financial | hisaab_master | Weekly settlement cycle master | In Review | No | Auto Created | No |  |  | Hisaab entries will be automatically created based on the week number.
| hisaab | Weekly settlement detail for a Driver, Vehicle, or Partner. | In Review | No | Derived | No |  |  | Only MUM Hisaab data has been shared. Could you please share the data for other cities as well, so we can verify whether the format is consistent across all cities? Please include data for all previous weeks.
Layer 5 — Analytics and Views
Layer 5 — Analytics and Views | daily_driver_ledger | Daily driver performance summary. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| challan_driver_view | Resolved mapping of challans to the responsible driver. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| daily_vehicle_ledger | Daily vehicle KPI snapshot. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| daily_partner_ledger | Daily partner-level financial aggregation. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| fleet_performance_daily | City-level fleet KPI snapshot per day. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| maintenance_summary | Monthly maintenance summary per vehicle. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.
| daily_rental_log | Daily rent computation log based on base plan and active discounts. | In Review | No | Derived | No |  |  | These are views that will primarily be used for analytics and tracking.

## Hisaab
Module Name | Status | Details
Allocation Master (allocation_master) | Completed | Resolves the Operator vs Individual classification issue by automatically consolidating multiple vehicles under a single operator for payout calculations.
Uber Raw Data (uber_raw) | Completed | Processes trip-level data to calculate Active Days and Uber KM, restricted to the vendor's allocation period.
Uber Payments (uber_payment_organisation) | Completed | Extracts Total Revenue, Cash Collected, Tolls, and Driver Subscription Charges.
Uber Incentives (uber_incentive) | Completed | Captures weekly incentive payouts and incorporates them into driver earnings.
Challan Fines (challan) | Completed | Charges challans based on exact vehicle allocation dates, ensuring fines are assigned only to the responsible driver.
Accident Penalties (accident_penalty) | Completed | Applies accident penalties using allocation date matching to ensure penalties are assigned to the correct driver.
TDS Logic | Completed | Calculates 1% TDS for standard drivers and automatically exempts identified operators.
Current Week O/S (Master Calculator) | Completed | Calculates the final weekly outstanding amount by combining rent, earnings, challans, accident penalties, and TDS.
Dynamic Rent / Plan Master | Pending | Logic required to dynamically determine applicable daily rent rates based on vehicle, driver, and plan history. Currently using a fixed rent value.
Vehicle Level Adjustments | Completed | Adjustment framework required to process manual vehicle-level credits and debits.
Pending Due | Completed | Logic required to carry forward unpaid balances from previous periods and calculate cumulative outstanding amounts.
GPS Tracking & Dead Miles | Completed | Awaiting GPS/IoT data integration to calculate total GPS kilometers and dead kilometer penalties.
Onroad Days Logic | Pending | Awaiting final business rules for holiday and vehicle grounding scenarios before implementation.
Ola Raw Data & Incentives | Pending | Awaiting Ola source files (Trips, Revenue, Online Payments, and Incentives) to build the Ola calculation engine.

## Hisaab Data Required
Data Point | Status | Details | Remarks
Accident / Accident Penalty Data | Source Not Available | Accident penalty data is required in Hisaab; however, no master source or table is currently available for accident-level penalties or complete accident details. | For the accident table in the database, vehicle accidents have been identified using the Maintenance In & Out sheet, where repair types such as "Accident Paid" and "Accident Insurance" are treated as accident indicators.
Challan Data | Source Not Available | Challan data is currently unavailable in any source system. | Challans have been assumed for certain vehicles based on available Hisaab data. Actual challan-level data will be incorporated once the Challan API integration is completed.
Allocation-Level Data | Shared on 18 June | Allocation-level data has been received. | Data import and integration are currently pending.
Uber Data | API Not Available; Sample Data Available | A one-week sample dataset from Bengaluru was used for Hisaab development and validation. | Sample data has been loaded into the database for Bengaluru vehicles. Full API integration is pending.
Vehicle-Level Adjustments | Source Not Available | No source is available for vehicle-level adjustment data. | Placeholder data has been used by assuming weekly adjustments such as half-days, leaves, holidays, holds, etc.
GPS Data | Available | GPS data is available through Intellicar. | Weekly Intellicar data has been used. Some inconsistencies exist in vehicle number formatting and capture across records.
Dynamic Rent | Shared on 18 June | City-level and vendor-level dynamic rent data has been shared for incorporation into Hisaab. | Currently, a flat rent of ₹1,000 has been assumed until the dynamic rent logic is implemented.
On-Road Days | Master Data Not Available | No master data source is available for on-road day adjustments. | Not yet incorporated into Hisaab calculations.
OLA / Rapido Data | Source Not Available | No source or integration is currently available for OLA and Rapido data. | Not yet incorporated into Hisaab calculations.

## Requests
Data Requested | Comments | Received or Not | Critical
List of all locations where inspections are conducted | Received PDI inspection items, but details for other inspection locations/processes (e.g., swap, pre-maintenance, post-maintenance) were not provided. - Want a list of where actually inspection can happen? | Partial | Yes
Vehicle-level details for all vehicles to populate master vehicle table (registration date, onboarding date etc.) | Received on 18/06. (we are good) | Yes | Yes
Vehicle compliance document list and supporting documents | 18/06: Received the compliance document checklist, but actual vehicle documents were not provided. | Partial | No
Permissions and roles | Roles and permissions list received. | Yes
LetzRyd employee list with roles | 19/06: VVK : Not received. ( But Not Critical). We could manage with what we have | Ongoing | No
Hubs and parking information | Received on 18/06. (we are good) | Yes | Yes
Rental plans (based on age, vehicle, driver, etc.) | Received on 18/06. (we are evaluating) | Yes | Yes
List of all partners/vendors (driver providers) | 19/06: VVK : Received on 19/06. We are good/we evaluating | Yes | Yes
Workshop details (name, location, GST, contact information, etc.) | Not received. | No
Challan API details | Not received. | No
Uber/OLA/Rapido API | Not received. | No | Yes
Intellicar GPS API | Received. (we are good) | Yes
GoMyGPS | Not received. | No

## Independent
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated | Blockers / Comments
events
events | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
events | event_code | varchar | MANDATORY | Unique; Not Null | Not Available | Partial | Please provide the complete list of event codes and naming convention.
events | event_name | varchar | MANDATORY | Unique; Not Null | Not Available | Partial | Please provide the complete list of event names and their corresponding event codes.
events | entity_type | varchar | MANDATORY |  | Not Available | Partial | Please provide all supported entity types and their definitions.
events | category | varchar | OPTIONAL |  | Not Available | Partial | Please provide the list of event categories and category mapping rules.
events | description | text | OPTIONAL |  | Not Available | Partial | Please confirm whether descriptions are required and provide expected format/content guidelines.
events | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
events | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
pdi_types
pdi_types | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
pdi_types | name | varchar | MANDATORY | Unique; Not Null | Not Available | No | Please provide the complete list of inspection types/stages (e.g., Swap, Jama, Drop-off, Allocation) and naming convention.
pdi_types | description | text | OPTIONAL |  | Not Available | No | Please provide the definition and purpose of each inspection type.
pdi_types | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
pdi_types | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
permissions
permissions | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
permissions | permission_name | varchar | MANDATORY | Unique; Not Null | Not Available | No | Please provide the complete list of permissions and naming convention.
permissions | can_view_dashboard | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_edit_trips | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_import_data | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_edit_drivers | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_edit_vehicles | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_edit_assignments | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_view_financials | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_approve_hisaab | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_approve_invoices | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_edit_adjustments | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_approve_adjustments_ops | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_approve_adjustments_fin | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_manage_challans | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_manage_maintenance | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_manage_users | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_manage_partners | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | can_view_reports | boolean | MANDATORY | Default: false | Not Available | No | Please confirm whether this permission is required and which roles/departments should have access.
permissions | description | text | OPTIONAL |  | Not Available | No | Please provide the purpose and usage of each permission group.
permissions | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
permissions | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
roles
roles | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
roles | role_name | varchar | MANDATORY | Unique; Not Null | Not Available | No | Please provide the complete list of roles and naming convention.
roles | access_level | varchar | MANDATORY |  | Not Available | No | Please provide the list of access levels and their definitions.
roles | permission_id | integer | MANDATORY | FK → permissions.id | Not Available | No | Please provide the role-to-permission mapping and confirm whether a role can have multiple permissions.
roles | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
roles | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
users
users | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
users | email | varchar | MANDATORY | Unique; Not Null | Not Available | No | Please provide the list of all user email IDs.
users | password_hash | varchar | MANDATORY | Not Null | Not Available | No | Please confirm the authentication mechanism and password hashing approach.
users | first_name | varchar | MANDATORY |  | Not Available | Partial | Please provide the first name of all users.
users | last_name | varchar | OPTIONAL |  | Not Available | Partial | Please provide the last name of all users, if applicable.
users | phone | varchar | OPTIONAL |  | Not Available | No | Please provide user phone numbers and validation requirements.
users | department | varchar | OPTIONAL |  | Not Available | No | Please provide the list of departments and department mapping for all users.
users | role_id | integer | MANDATORY | FK → roles.id | Not Available | No | Please provide the user-to-role mapping.
users | access_level | varchar | MANDATORY |  | Not Available | No | Please provide the list of access levels and their definitions.
users | status | varchar | MANDATORY | Default: 'Active' | Not Available | No | Please provide the list of supported user statuses (e.g., Active, Inactive, Suspended).
users | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
users | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
cities
cities | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Yes | Auto-generated primary key.
cities | name | varchar | MANDATORY | Unique; Not Null | Available | Yes | Bengaluru, Hyderabad, Mumbai.
cities | state | varchar | OPTIONAL |  | Available | Yes | Karnataka, Telangana, Maharashtra.
cities | status | varchar | MANDATORY | Default: 'Active' | Available | Yes | Active for all available cities.
cities | created_at | timestamp | MANDATORY |  | Auto Created | Yes | Auto-generated timestamp. No clarification required.
cities | modified_at | timestamp | OPTIONAL |  | Auto Created | Yes | Auto-generated timestamp.
hubs_and_parking
hubs_and_parking | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
hubs_and_parking | name | varchar | MANDATORY | Not Null | Not Available | Partial | Placeholder hub and parking names have been populated (e.g., Bengaluru Main Hub, Hyderabad Central Parking). Please provide the complete list of actual hubs and parking locations.
hubs_and_parking | city_id | integer | MANDATORY | FK → cities.id | Available | Partial | Mapped to available cities. Please confirm city-to-hub mapping and whether additional locations exist.
hubs_and_parking | address | text | OPTIONAL |  | Not Available | No | Please provide the complete address for each hub and parking location.
hubs_and_parking | pincode | varchar | OPTIONAL |  | Not Available | No | Please provide the pincode for each hub and parking location.
hubs_and_parking | type | varchar | MANDATORY |  | Not Available | Partial | Hub and Parking types populated. Please confirm if additional location types are required.
hubs_and_parking | capacity | integer | OPTIONAL |  | Not Available | No | Please provide capacity details for each hub and parking location, if applicable.
hubs_and_parking | status | varchar | MANDATORY | Default: 'Active' | Not Available | Partial | Active for all available locations. Please confirm valid status values.
hubs_and_parking | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
hubs_and_parking | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
rental_plans
rental_plans | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
rental_plans | city_id | integer | MANDATORY | FK → cities.id | Available | Partial | Mapped to available cities. Please provide actual city-to-rental-plan mapping. Current records contain dummy/sample data.
rental_plans | plan_name | varchar | MANDATORY | Not Null | Not Available | Partial | Placeholder plans populated (e.g., Bengaluru Standard Plan, Hyderabad Standard Plan). Please provide actual rental plan names.
rental_plans | description | text | OPTIONAL |  | Not Available | Partial | Placeholder descriptions populated ("System generated baseline plan. Pending master rates."). Please provide actual plan descriptions.
rental_plans | daily_rate | decimal | OPTIONAL |  | Not Available | No | Please provide actual daily rental rates.
rental_plans | weekly_rate | decimal | OPTIONAL |  | Not Available | No | Please provide actual weekly rental rates.
rental_plans | monthly_rate | decimal | OPTIONAL |  | Not Available | No | Please provide actual monthly rental rates.
rental_plans | vehicle_type | varchar | OPTIONAL |  | Not Available | Partial | 4W populated for all plans. Please confirm supported vehicle types and mappings.
rental_plans | status | varchar | MANDATORY | Default: 'Active' | Not Available | Partial | Active for all available plans. Please confirm valid status values.
rental_plans | plan_active | boolean | MANDATORY | Default: true | Not Available | No | Please confirm activation logic and provide values.
rental_plans | apply_vehicle_age_discount | boolean | MANDATORY | Default: false | Not Available | No | Please provide vehicle age discount rules and values.
rental_plans | base_plan_id | integer | OPTIONAL | FK → rental_plans.id | Not Available | No | Please confirm whether plan versioning is required.
rental_plans | version_number | integer | OPTIONAL | Default: 1 | Not Available | No | Please provide versioning rules and values, if applicable.
rental_plans | ops_approval_status | varchar | OPTIONAL | Default: 'Pending' | Not Available | No | Please provide operations approval workflow and valid statuses.
rental_plans | ops_approved_by_user_id | integer | OPTIONAL | FK → users.id | Not Available | No | Please provide approver mapping rules and values.
rental_plans | ops_approved_at | timestamp | OPTIONAL |  | Not Available | No | Please provide approval timestamps.
rental_plans | driver_approval_status | varchar | OPTIONAL | Default: 'Pending' | Not Available | No | Please provide driver approval workflow and valid statuses.
rental_plans | driver_approved_at | timestamp | OPTIONAL |  | Not Available | No | Please provide approval timestamp rules and values.
rental_plans | effective_from | date | OPTIONAL |  | Not Available | No | Please provide plan effective date rules and values.
rental_plans | effective_to | date | OPTIONAL |  | Not Available | No | Please provide plan expiry/end date rules and values.
rental_plans | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
rental_plans | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
car_age_rental_discount_master
car_age_rental_discount_master | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
car_age_rental_discount_master | car_model | varchar | MANDATORY | Not Null | Not Available | No | Please provide the list of car models eligible for age-based rental discounts.
car_age_rental_discount_master | car_age_in_years | integer | MANDATORY | Not Null | Not Available | No | Please provide the car age slabs and corresponding discount rules.
car_age_rental_discount_master | discount_applied | decimal | MANDATORY | Not Null | Not Available | No | Please provide the discount percentage/amount applicable for each car age slab.
car_age_rental_discount_master | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
car_age_rental_discount_master | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
partners
partners | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
partners | partner_code | varchar | MANDATORY | Unique; Not Null | Not Available | No | No system issue, but requires mapping with partner_id for legacy records
partners | name | varchar | MANDATORY | Not Null | Available | Yes | No major data issue
partners | type | varchar | MANDATORY | Not Null | Available | Yes | No major data issue
partners | phone | varchar | MANDATORY | Unique; Not Null | Available | Yes | No major data issue
partners | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major data issue
partners | status | varchar | MANDATORY | Default: 'Active' | Available | Yes | Default value is set to 'Active'. Confirmation needed on whether this field is required or can be deprecated.
partners | rental_plan_id | integer | OPTIONAL | FK → rental_plans.id | Not Available | No | Source for rental plans is not available; needs clarification or data source definition.
partners | refundable_deposit | decimal | OPTIONAL |  | Not Available | No | Needs confirmation if this field is required.
partners | onetime_joining_fee | decimal | OPTIONAL |  | Not Available | No | Needs confirmation if this field is required.
partners | deposit_paid | decimal | OPTIONAL |  | Available | Yes | No major data issue
partners | pending_deposit | decimal | OPTIONAL |  | Not Available | No | Needs confirmation if this field is required.
partners | onboarding_date | date | OPTIONAL |  | Available | Yes | No major data issue
partners | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
partners | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
drivers
drivers | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated; no blockers
drivers | driver_code | varchar | MANDATORY | Unique; Not Null | Available | Yes | No system issue – needs mapping with DriverID for old records/Duplicate driver id exists in some records
drivers | partner_id | integer | OPTIONAL | FK → partners.id | Not Available | No | Please provide data source for partner-driver relationship
drivers | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major data issue
drivers | walkin_lead_id | integer | OPTIONAL | FK → walkin_leads.id | Available | Yes | No major issues – present only for limited records
drivers | onboarding_id | integer | OPTIONAL | FK → driver_onboarding.id | Available | Yes | No major data issue
drivers | first_name | varchar | MANDATORY | Not Null | Available | Yes | Name quality issue: single-name or full-name misplacement observed (6.9%)
drivers | last_name | varchar | OPTIONAL |  | Available | Partial | Often NULL or merged into first_name → inconsistent name normalization
drivers | phone | varchar | MANDATORY | Not Null | Available | Yes | 12 invalid phone entries detected → digit length inconsistencies
drivers | whatsapp_number | varchar | OPTIONAL |  | Available | Yes
drivers | father_name | varchar | OPTIONAL |  | Available | Yes
drivers | dob | date | OPTIONAL |  | Available | Yes | Underage drivers (1.0%) + unparsable DOB (0.2%) → invalid/corrupted date entries
drivers | status | varchar | MANDATORY | Default: 'Active' | Not Available | No | Please provide list of Active / Inactive / Suspended drivers
drivers | aadhaar_number | varchar | MANDATORY | Unique | Available | Yes | Invalid Aadhaar entries (4 cases) + missing values → KYC completeness gap
drivers | pan_number | varchar | MANDATORY | Unique | Available | Yes | Invalid PAN formats (13 entries) → compliance validation failures
drivers | dl_number | varchar | MANDATORY | Unique | Available | Yes | Duplicate DL numbers (51 cases) → uniqueness violation
drivers | pan_aadhaar_linked | boolean | OPTIONAL | Default: false | Available | Yes | Not consistently updated → cannot be used reliably for compliance decisions
drivers | address_as_per_aadhaar | text | MANDATORY |  | Available | Yes | Free-text inconsistencies; formatting varies across records
drivers | present_address | text | OPTIONAL |  | Available | Yes | Often duplicated or inconsistent with Aadhaar address → weak normalization
drivers | permanent_address | text | OPTIONAL |  | Available | Yes | Free-text inconsistencies; formatting varies across records
drivers | emergency_name | varchar | OPTIONAL |  | Available | Yes | No major issues
drivers | emergency_phone | varchar | OPTIONAL |  | Available | Yes | No major issues
drivers | bank_account_name | varchar | OPTIONAL |  | Available | Yes | No major issues
drivers | account_no | varchar | OPTIONAL |  | Available | Yes | Invalid account numbers (19 entries) → fails 9–18 digit validation
drivers | ifsc_code | varchar | OPTIONAL |  | Available | Yes | Invalid IFSC codes (51 entries) → non-standard formats detected
drivers | upi_id | varchar | OPTIONAL |  | Available | Yes | High error rate (20.4% / 313 entries) → phone numbers or invalid strings used instead of valid UPI format
drivers | bank_verified_status | varchar | MANDATORY | Default: 'Pending' | Not Available | No | Data source not present
drivers | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
drivers | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
driver_documents
driver_documents | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
driver_documents | driver_id | integer | MANDATORY | Not Null; FK → drivers.id | Available | Yes | Mapped to drivers table.
driver_documents | onboarding_id | integer | OPTIONAL | FK → driver_onboarding.id | Available | Yes | Mapped to onboarding flow.
driver_documents | document_type | varchar | MANDATORY | Not Null | Available | Yes | Document types stored; front/back stored as separate records
driver_documents | document_number | varchar | OPTIONAL |  | Available | Partial | Some NULL may exist; available mainly for DL/PAN, missing for selfie/address proof
driver_documents | issued_date | date | OPTIONAL |  | Not Available | No | Not captured for most documents; needs confirmation if required
driver_documents | expiry_date | date | OPTIONAL |  | Available | Partial | Available mainly for DL; missing for other document types
driver_documents | issuing_authority | varchar | OPTIONAL |  | Not Available | No | Not currently captured; confirm if required
driver_documents | document_url | varchar | MANDATORY | Not Null | Available | Yes | No major issues; stores uploaded document reference
driver_documents | verification_status | varchar | MANDATORY | Default: 'Pending' | Not Available | Yes | No verification process implemented yet; confirm if required
driver_documents | verified_by_user_id | integer | OPTIONAL | FK → users.id | Not Available | No | Not implemented; confirm if required
driver_documents | verified_at | timestamp | OPTIONAL |  | Not Available | No | Not implemented; confirm if required
driver_documents | rejection_reason | varchar | OPTIONAL |  | Not Available | No | Not implemented; confirm if required
driver_documents | is_current | boolean | MANDATORY | Default: true | Not Available | No | Not implemented; confirm if required
driver_documents | remarks | text | OPTIONAL |  | Not Available | Yes | Not implemented; confirm if required
driver_documents | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
driver_documents | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
vehicles
vehicles | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
vehicles | vehicle_number | varchar | MANDATORY | Unique; Not Null | Available | Yes | No major issues
vehicles | vin_number | varchar | MANDATORY | Unique | Not Available | No | VIN not captured in current system
vehicles | registration_date | date | MANDATORY |  | Not Available | No | Registration date not captured
vehicles | vehicle_model | varchar | MANDATORY | Not Null | Available | Yes | No major issues
vehicles | vehicle_brand | varchar | MANDATORY | Not Null | Available | Yes | No major issues
vehicles | vehicle_type | varchar | MANDATORY | Not Null | Available | Yes | No major issues
vehicles | fuel_type | varchar | MANDATORY |  | Available | Yes | No major issues
vehicles | is_ac | boolean | MANDATORY | Default: true | Not Available | No | AC flag not captured
vehicles | seating_capacity | integer | MANDATORY |  | Available | Yes | No major issues
vehicles | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major issues
vehicles | rental_plan_id | integer | OPTIONAL | FK → rental_plans.id | Not Available | No | Rental plan mapping not available
vehicles | current_status | varchar | MANDATORY | Default: 'Idle' | Available | Yes | No major issues
vehicles | date_added | date | MANDATORY |  | Not Available | No | Date added not populated
vehicles | fasttag_balance | decimal | OPTIONAL |  | Not Available | No | FASTag balance not tracked
vehicles | rc_url | varchar | MANDATORY |  | Not Available | No | Not Available
vehicles | insurance_url | varchar | MANDATORY |  | Not Available | No | Not Available
vehicles | permit_url | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicles | fitness_url | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicles | emission_url | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicles | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
vehicles | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
vehicle_compliance
vehicle_compliance | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
vehicle_compliance | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | No | Not Available
vehicle_compliance | compliance_type | varchar | MANDATORY | Not Null | Not Available | No | Not Available
vehicle_compliance | certificate_number | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | issued_date | date | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | expiry_date | date | MANDATORY | Not Null | Not Available | No | Not Available
vehicle_compliance | issuing_authority | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | document_url | varchar | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | status | varchar | MANDATORY | Default: 'Active' | Not Available | No | Not Available
vehicle_compliance | alert_triggered | boolean | MANDATORY | Default: false | Not Available | No | Not Available
vehicle_compliance | alert_sent_at | timestamp | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | renewed_compliance_id | integer | OPTIONAL | FK → vehicle_compliance.id | Not Available | No | Not Available
vehicle_compliance | remarks | text | OPTIONAL |  | Not Available | No | Not Available
vehicle_compliance | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
vehicle_compliance | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
workshops
workshops | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
workshops | name | varchar | MANDATORY | Not Null | Not Available | Yes | Needs to be pulled from vehicle maintenance sheet; no master source exists
workshops | city_id | integer | MANDATORY | FK → cities.id | Not Available | No | Not Available
workshops | address | text | OPTIONAL |  | Not Available | No | Not Available
workshops | pincode | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | contact_person | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | phone | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | gst_number | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | type | varchar | MANDATORY |  | Not Available | No | Not Available
workshops | brand_type | varchar | MANDATORY |  | Not Available | No | Not Available
workshops | supported_brands | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | supported_vehicle_types | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | supported_models | varchar | OPTIONAL |  | Not Available | No | Not Available
workshops | status | varchar | MANDATORY | Default: 'Active' | Not Available | No | Not Available
workshops | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
workshops | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
walkin_leads
walkin_leads | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
walkin_leads | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major issues
walkin_leads | event_date | date | MANDATORY |  | Available | Yes | No major issues
walkin_leads | attending_executive_user_id | integer | OPTIONAL | FK → users.id | Available | Yes | Names to be cleaned
walkin_leads | partner_name | varchar | OPTIONAL |  | Available | Yes | No major issues
walkin_leads | partner_number | varchar | OPTIONAL |  | Available | Yes | No major issues
walkin_leads | dl_number | varchar | OPTIONAL |  | Available | Yes | No major issues
walkin_leads | visiting_reason | varchar | OPTIONAL |  | Available | Yes | No major issues
walkin_leads | remarks | text | OPTIONAL |  | Available | Yes | No major issues
walkin_leads | joined_status | varchar | OPTIONAL |  | Available | Partial | FALSE AND NULL at all places
walkin_leads | joined_date | date | OPTIONAL |  | Not Available | No | Not Available
walkin_leads | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
walkin_leads | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
driver_onboarding
driver_onboarding | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
driver_onboarding | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major issues
driver_onboarding | walkin_lead_id | integer | OPTIONAL | FK → walkin_leads.id | Available | Yes | No major issues
driver_onboarding | event_date | date | MANDATORY |  | Available | Yes | No major issues
driver_onboarding | attending_executive_user_id | integer | OPTIONAL | FK → users.id | Available | Yes | No major issues
driver_onboarding | driver_name | varchar | MANDATORY |  | Available | Yes | No major issues
driver_onboarding | driver_phone | varchar | MANDATORY |  | Available | Yes | Some duplicates observed; needs dedup validation.
driver_onboarding | dl_number | varchar | MANDATORY |  | Available | Yes | Some invalid formats and duplicates exist.
driver_onboarding | onboarding_type | varchar | MANDATORY |  | Available | Yes | No major issues
driver_onboarding | lead_source | varchar | OPTIONAL |  | Available | Yes | No major issues
driver_onboarding | onboarding_date | date | OPTIONAL |  | Available | Yes | No major issues
driver_onboarding | onboarding_status | varchar | MANDATORY |  | Available | Yes | No major issues (default - active)
driver_onboarding | is_bgv_cleared | boolean | MANDATORY | Default: false | Optional |  | Not implemented; confirm if required
driver_onboarding | is_training_completed | boolean | MANDATORY | Default: false | Optional |  | Not implemented; confirm if required
driver_onboarding | is_kit_issued | boolean | MANDATORY | Default: false | Optional |  | Not implemented; confirm if required
driver_onboarding | remarks | text | OPTIONAL |  | Optional |  | Not implemented; confirm if required
driver_onboarding | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
driver_onboarding | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto-generated timestamp.
gps_log
gps_log | id | bigint | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
gps_log | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | Yes | No major issues
gps_log | gps_vendor | varchar | MANDATORY |  | Available | Yes | No major issues
gps_log | event_date | timestamp | MANDATORY | Not Null | Available | Yes | No major issues
gps_log | latitude | decimal | OPTIONAL |  | Available | No | Not implemented; confirm if required
gps_log | longitude | decimal | OPTIONAL |  | Available | No | Not implemented; confirm if required
gps_log | speed_kmph | decimal | OPTIONAL |  | Not Available | No | Not implemented
gps_log | heading_degrees | decimal | OPTIONAL |  | Not Available | No | Not implemented
gps_log | accuracy_metres | decimal | OPTIONAL |  | Not Available | No | Not implemented
gps_log | distance_covered_since_last_ping | decimal | OPTIONAL |  | Available | Yes | No major issues
gps_log | cumulative_distance | decimal | OPTIONAL |  | Not Available | No | Not implemented
gps_log | ignition_status | varchar | OPTIONAL |  | Not Available | No | Not implemented; confirm if required
gps_log | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp. No clarification required.
challan_logs
challan_logs | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto-generated primary key.
challan_logs | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | Yes | No major issues
challan_logs | driver_id | integer | OPTIONAL | FK → drivers.id | Available | Yes | Challan Not Linked to Driver Directly , Please provide source
challan_logs | vehicle_number | varchar | MANDATORY |  | Available | Yes | No major issues
challan_logs | challan_number | varchar | MANDATORY |  | Not Available | No | Source not available.
challan_logs | challan_date | timestamp | MANDATORY |  | Not Available | No | Source not available.
challan_logs | amount | decimal | MANDATORY |  | Available | Yes | No major issues
challan_logs | violation_rule | varchar | OPTIONAL |  | Not Available | No | No major issues
challan_logs | location | text | OPTIONAL |  | Not Available | No | No major issues
challan_logs | status | varchar | MANDATORY |  | Not Available | Yes | Default: ‘Unpaid’ — needs confirmation if this is required. Source not available.
challan_logs | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto-generated timestamp.

## Dependent
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated/QC | Blockers / Comments
jama_logs
jama_logs | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
jama_logs | assignment_id | integer | MANDATORY | FK → vehicle_assignments.id | Available | No | Need Jama Form Data
jama_logs | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | No | Need Jama Form Data
jama_logs | driver_id | integer | OPTIONAL | FK → drivers.id | Available | No | Need Jama Form Data
jama_logs | hub_id | integer | OPTIONAL | FK → hubs_and_parking.id | Not Available | No | Need Jama Form Data
jama_logs | event_date | timestamp | MANDATORY | Not Null | Available | No | Need Jama Form Data
jama_logs | surrender_reason | varchar | OPTIONAL |  | Not Available | No | Need Jama Form Data
jama_logs | jama_status | varchar | MANDATORY | Default: 'Pending PDI' | Not Available | No | Need Jama Form Data
jama_logs | pdi_id | integer | OPTIONAL | FK → pdi_logs.id | Not Available | No | Need Jama Form Data
jama_logs | pdi_done_by_user_id | integer | OPTIONAL | FK → users.id | Not Available | No | Need Jama Form Data
jama_logs | pdi_date | timestamp | OPTIONAL |  | Not Available | No | Need Jama Form Data
jama_logs | is_ready_for_deployment | boolean | MANDATORY | Default: false | Not Available | No | Need Jama Form Data
jama_logs | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
jama_logs | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto Created
vehicle_states
vehicle_states | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
vehicle_states | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | No | Current Status of Vehicle
vehicle_states | state_name | varchar | MANDATORY | Not Null | Available | No | Current Status of Vehicle
vehicle_states | sub_state | varchar | OPTIONAL |  | Available | No | Current Status of Vehicle
vehicle_states | entered_at | timestamp | MANDATORY | Not Null | Available | No | Current Status of Vehicle
vehicle_states | exited_at | timestamp | OPTIONAL |  | Available | No | Current Status of Vehicle
vehicle_states | is_current | boolean | MANDATORY | Default: true | Available | No | Current Status of Vehicle
vehicle_states | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
car_rental_discount
car_rental_discount | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
car_rental_discount | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | discount_amount | decimal | MANDATORY | Not Null | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | reason | varchar | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | effective_from | date | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | effective_to | date | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | is_active | boolean | MANDATORY | Default: true | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
car_rental_discount | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
car_rental_discount | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto Created
driver_rental_discount
driver_rental_discount | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
driver_rental_discount | driver_id | integer | MANDATORY | Not Null; FK → drivers.id | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | discount_amount | decimal | MANDATORY | Not Null | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | reason | varchar | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | effective_from | date | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | effective_to | date | OPTIONAL |  | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | is_active | boolean | MANDATORY | Default: true | Not Available | No | This table will be used to create vehicle-specific rental discounts. Please confirm whether this table is required.
driver_rental_discount | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
driver_rental_discount | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto Created
data_imports
data_imports | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
data_imports | platform | varchar | MANDATORY |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | file_name | varchar | MANDATORY | Not Null | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | file_type | varchar | MANDATORY |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | parsing_method | varchar | MANDATORY |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | uploaded_by_user_id | integer | OPTIONAL | FK → users.id | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | event_date | timestamp | MANDATORY |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | total_rows | integer | OPTIONAL |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | successful_rows | integer | OPTIONAL |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | error_rows | integer | OPTIONAL |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | is_success | boolean | MANDATORY | Default: false | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | error_details | json | OPTIONAL |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | status | varchar | MANDATORY |  | Auto Created | Auto Created | Any data imported into the database in production after deployment will be tracked in this table.
data_imports | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
data_imports | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto Created
user_roles
user_roles | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
user_roles | user_id | integer | MANDATORY | Not Null; FK → users.id |  |  | This will be used to support multiple roles per user.
user_roles | role_id | integer | MANDATORY | Not Null; FK → roles.id |  |  | This will be used to support multiple roles per user.
user_roles | assigned_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
vehicle_assignments
vehicle_assignments | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment | Auto Created | Auto Created | Auto Created
vehicle_assignments | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id | Available | Yes | No major issues
vehicle_assignments | partner_id | integer | OPTIONAL | FK → partners.id | Not Available | No | We should be able to link each vehicle assignment to both a driver and a partner. Please confirm whether this association is required.
vehicle_assignments | driver_id | integer | OPTIONAL | FK → drivers.id | Available | Yes | No major issues
vehicle_assignments | parking_id | integer | OPTIONAL | FK → hubs_and_parking.id | Not Available | No | Parking and hub information is currently missing. If vehicles can be assigned to parking, please provide the required data source.
vehicle_assignments | workshop_id | integer | OPTIONAL | FK → workshops.id | Not Available | No | Workshop-related information is not available. If vehicles can be assigned to workshops, please share the data source.
vehicle_assignments | city_id | integer | MANDATORY | FK → cities.id | Available | Yes | No major issues
vehicle_assignments | swap_group_id | varchar | OPTIONAL |  | Not Available | No | Swap-related information is missing. Please confirm the source and structure for swap group data.
vehicle_assignments | assignment_type | varchar | MANDATORY |  | Available | Yes | Assignment type: Currently only “allocation” and “drop off” values are available. Please provide additional assignment types that are required .
vehicle_assignments | event_date | timestamp | MANDATORY | Not Null | Available | Yes | No major issues
vehicle_assignments | driver_plan | varchar | OPTIONAL |  | Available | Yes | No major issues
vehicle_assignments | start_kms | integer | OPTIONAL |  | Not Available | No | These fields are not currently available. Please confirm whether tracking start and end odometer readings is required.
vehicle_assignments | end_kms | integer | OPTIONAL |  | Not Available | No | These fields are not currently available. Please confirm whether tracking start and end odometer readings is required.
vehicle_assignments | agreement_file | varchar | OPTIONAL |  | Not Available | No | These fields are not currently available. Please confirm whether tracking start and end odometer readings is required.
vehicle_assignments | assignment_reason | varchar | OPTIONAL |  | Not Available | No | These fields are not currently available. Please confirm whether tracking start and end odometer readings is required.
vehicle_assignments | status | varchar | MANDATORY |  | Available | Yes | Currently defaults to “active”. Please confirm whether additional statuses are needed beyond active/inactive or if a different status model is required.
vehicle_assignments | created_at | timestamp | MANDATORY |  | Auto Created | Auto Created | Auto Created
vehicle_assignments | modified_at | timestamp | OPTIONAL |  | Auto Created | Auto Created | Auto Created
pdi_logs
pdi_logs | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
pdi_logs | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
pdi_logs | driver_id | integer | OPTIONAL | FK → drivers.id
pdi_logs | assignment_id | integer | OPTIONAL | FK → vehicle_assignments.id
pdi_logs | pdi_type_id | integer | MANDATORY | FK → pdi_types.id
pdi_logs | inspected_by_user_id | integer | OPTIONAL | FK → users.id
pdi_logs | event_date | timestamp | MANDATORY
pdi_logs | photo_front | varchar | OPTIONAL
pdi_logs | photo_lh | varchar | OPTIONAL
pdi_logs | photo_rh | varchar | OPTIONAL
pdi_logs | photo_back | varchar | OPTIONAL
pdi_logs | photo_battery | varchar | OPTIONAL
pdi_logs | is_stepney_present | boolean | OPTIONAL
pdi_logs | is_jack_present | boolean | OPTIONAL
pdi_logs | is_spanner_present | boolean | OPTIONAL
pdi_logs | is_fire_extinguisher_present | boolean | OPTIONAL
pdi_logs | is_documents_present | boolean | OPTIONAL
pdi_logs | pdi_status | varchar | MANDATORY
pdi_logs | remarks | text | OPTIONAL
pdi_logs | is_ready_for_deployment | boolean | MANDATORY | Default: false
pdi_logs | created_at | timestamp | MANDATORY
pdi_logs | modified_at | timestamp | OPTIONAL
maintenance_pipeline
maintenance_pipeline | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
maintenance_pipeline | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
maintenance_pipeline | workshop_id | integer | MANDATORY | Not Null; FK → workshops.id
maintenance_pipeline | accident_id | integer | OPTIONAL | FK → accidents.id
maintenance_pipeline | city_id | integer | MANDATORY | FK → cities.id
maintenance_pipeline | event_date | timestamp | MANDATORY | Not Null
maintenance_pipeline | start_date | timestamp | OPTIONAL
maintenance_pipeline | end_date | timestamp | OPTIONAL
maintenance_pipeline | vehicle_kms | integer | OPTIONAL
maintenance_pipeline | repair_type | varchar | MANDATORY
maintenance_pipeline | mode_of_repair | varchar | OPTIONAL
maintenance_pipeline | final_status | varchar | MANDATORY
maintenance_pipeline | created_at | timestamp | MANDATORY
maintenance_pipeline | modified_at | timestamp | OPTIONAL
maintenance_logs
maintenance_logs | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
maintenance_logs | maintenance_pipeline_id | integer | MANDATORY | Not Null; FK → maintenance_pipeline.id
maintenance_logs | stage | varchar | MANDATORY
maintenance_logs | performed_by_user_id | integer | OPTIONAL | FK → users.id
maintenance_logs | event_date | timestamp | MANDATORY | Not Null
maintenance_logs | remarks | text | OPTIONAL
maintenance_logs | created_at | timestamp | MANDATORY
maintenance_logs | modified_at | timestamp | OPTIONAL
maintenance_invoices
maintenance_invoices | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
maintenance_invoices | maintenance_pipeline_id | integer | MANDATORY | Not Null; FK → maintenance_pipeline.id
maintenance_invoices | invoice_number | varchar | MANDATORY
maintenance_invoices | event_date | date | MANDATORY
maintenance_invoices | amount | decimal | MANDATORY
maintenance_invoices | tax_amount | decimal | OPTIONAL
maintenance_invoices | total_amount | decimal | MANDATORY
maintenance_invoices | file_url | varchar | MANDATORY
maintenance_invoices | payment_status | varchar | MANDATORY | Default: 'Pending'
maintenance_invoices | paid_date | date | OPTIONAL
maintenance_invoices | utr_number | varchar | OPTIONAL
maintenance_invoices | approved_by_user_id | integer | OPTIONAL | FK → users.id
maintenance_invoices | created_at | timestamp | MANDATORY
maintenance_invoices | modified_at | timestamp | OPTIONAL
accidents
accidents | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
accidents | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
accidents | driver_id | integer | OPTIONAL | FK → drivers.id
accidents | event_date | timestamp | MANDATORY | Not Null
accidents | location | varchar | OPTIONAL
accidents | fault_type | varchar | OPTIONAL
accidents | repair_type | varchar | OPTIONAL
accidents | estimate_amount | decimal | OPTIONAL
accidents | penalty_amount | decimal | OPTIONAL
accidents | insurance_claim_status | varchar | OPTIONAL
accidents | remarks | text | OPTIONAL
accidents | created_at | timestamp | MANDATORY
accidents | modified_at | timestamp | OPTIONAL
insurance_claims
insurance_claims | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
insurance_claims | accident_id | integer | MANDATORY | Not Null; FK → accidents.id
insurance_claims | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
insurance_claims | driver_id | integer | OPTIONAL | FK → drivers.id
insurance_claims | claim_reference_no | varchar | OPTIONAL
insurance_claims | insurer_name | varchar | MANDATORY
insurance_claims | policy_number | varchar | MANDATORY
insurance_claims | claim_filed_date | date | OPTIONAL
insurance_claims | surveyor_name | varchar | OPTIONAL
insurance_claims | survey_date | date | OPTIONAL
insurance_claims | estimated_amount | decimal | OPTIONAL
insurance_claims | approved_amount | decimal | OPTIONAL
insurance_claims | settlement_amount | decimal | OPTIONAL
insurance_claims | utr_number | varchar | OPTIONAL
insurance_claims | settled_date | date | OPTIONAL
insurance_claims | status | varchar | MANDATORY | Default: 'Not Filed'
insurance_claims | rejection_reason | text | OPTIONAL
insurance_claims | document_url | varchar | OPTIONAL
insurance_claims | remarks | text | OPTIONAL
insurance_claims | created_at | timestamp | MANDATORY
insurance_claims | modified_at | timestamp | OPTIONAL
media_attachments
media_attachments | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
media_attachments | entity_type | varchar | MANDATORY | Not Null
media_attachments | entity_id | integer | MANDATORY | Not Null
media_attachments | label | varchar | OPTIONAL
media_attachments | url | varchar | MANDATORY | Not Null
media_attachments | file_type | varchar | OPTIONAL
media_attachments | uploaded_by_user_id | integer | OPTIONAL | FK → users.id
media_attachments | uploaded_at | timestamp | MANDATORY | Not Null
media_attachments | created_at | timestamp | MANDATORY
tickets
tickets | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
tickets | partner_id | integer | OPTIONAL | FK → partners.id
tickets | driver_id | integer | OPTIONAL | FK → drivers.id
tickets | raised_by_user_id | integer | OPTIONAL | FK → users.id
tickets | assigned_to_user_id | integer | OPTIONAL | FK → users.id
tickets | event_date | timestamp | MANDATORY
tickets | issue_type | varchar | MANDATORY
tickets | description | text | MANDATORY
tickets | priority | varchar | MANDATORY | Default: 'Medium'
tickets | status | varchar | MANDATORY
tickets | resolution_notes | text | OPTIONAL
tickets | resolved_at | timestamp | OPTIONAL
tickets | created_at | timestamp | MANDATORY
tickets | modified_at | timestamp | OPTIONAL

## Ledger
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated/QC | Blockers / Comments
trips
trips | id | bigint | MANDATORY | PRIMARY KEY, Auto-Increment
trips | platform | varchar | MANDATORY
trips | transaction_uuid | varchar | OPTIONAL
trips | trip_uuid | varchar | MANDATORY | Unique; Not Null
trips | driver_uuid | varchar | OPTIONAL
trips | driver_name | varchar | OPTIONAL
trips | platform_vehicle_number | varchar | OPTIONAL
trips | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
trips | driver_id | integer | OPTIONAL | FK → drivers.id
trips | city_id | integer | MANDATORY | FK → cities.id
trips | event_date | timestamp | MANDATORY | Not Null
trips | pickup_time | timestamp | OPTIONAL
trips | dropoff_time | timestamp | OPTIONAL
trips | trip_distance_km | decimal | OPTIONAL
trips | duration_mins | decimal | OPTIONAL
trips | status | varchar | MANDATORY
trips | cancellation_reason | varchar | OPTIONAL
trips | gross_fare | decimal | OPTIONAL
trips | platform_commission | decimal | OPTIONAL
trips | net_payout | decimal | OPTIONAL
trips | cash_collected | decimal | OPTIONAL
trips | toll_parking | decimal | OPTIONAL
trips | taxes | decimal | OPTIONAL
trips | incentive | decimal | OPTIONAL
trips | cancellation_fee | decimal | OPTIONAL
trips | wait_time_charges | decimal | OPTIONAL
trips | refund_amount | decimal | OPTIONAL
trips | payment_type | varchar | OPTIONAL
trips | import_id | integer | OPTIONAL | FK → data_imports.id
trips | created_at | timestamp | MANDATORY
trips | modified_at | timestamp | OPTIONAL
adjustment_logs
adjustment_logs | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
adjustment_logs | hisaab_master_id | integer | OPTIONAL | FK → hisaab_master.id
adjustment_logs | city_id | integer | OPTIONAL | FK → cities.id
adjustment_logs | partner_id | integer | OPTIONAL | FK → partners.id
adjustment_logs | vehicle_id | integer | OPTIONAL | FK → vehicles.id
adjustment_logs | driver_id | integer | OPTIONAL | FK → drivers.id
adjustment_logs | event_date | date | MANDATORY | Not Null
adjustment_logs | adjustment_type | varchar | MANDATORY
adjustment_logs | remittance_towards | varchar | OPTIONAL
adjustment_logs | amount | decimal | MANDATORY | Not Null
adjustment_logs | photo_url | varchar | OPTIONAL
adjustment_logs | remarks | text | OPTIONAL
adjustment_logs | adjustment_related_to | varchar | OPTIONAL
adjustment_logs | ops_status | varchar | MANDATORY | Default: 'Pending'
adjustment_logs | finance_status | varchar | MANDATORY | Default: 'Pending'
adjustment_logs | created_at | timestamp | MANDATORY
adjustment_logs | modified_at | timestamp | OPTIONAL
driver_ledger
driver_ledger | id | bigint | MANDATORY | PRIMARY KEY, Auto-Increment
driver_ledger | driver_id | integer | MANDATORY | Not Null; FK → drivers.id
driver_ledger | vehicle_id | integer | OPTIONAL | FK → vehicles.id
driver_ledger | hisaab_master_id | integer | OPTIONAL | FK → hisaab_master.id
driver_ledger | event_id | integer | MANDATORY | Not Null; FK → events.id
driver_ledger | event_name | varchar | MANDATORY
driver_ledger | event_date | timestamp | MANDATORY | Not Null
driver_ledger | amount | decimal | OPTIONAL
driver_ledger | description | text | MANDATORY
driver_ledger | reference_id | integer | OPTIONAL
driver_ledger | reference_type | varchar | OPTIONAL
driver_ledger | created_at | timestamp | MANDATORY
vehicle_ledger
vehicle_ledger | id | bigint | MANDATORY | PRIMARY KEY, Auto-Increment
vehicle_ledger | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
vehicle_ledger | driver_id | integer | OPTIONAL | FK → drivers.id
vehicle_ledger | hisaab_master_id | integer | OPTIONAL | FK → hisaab_master.id
vehicle_ledger | event_id | integer | MANDATORY | Not Null; FK → events.id
vehicle_ledger | event_name | varchar | MANDATORY
vehicle_ledger | event_date | timestamp | MANDATORY | Not Null
vehicle_ledger | amount | decimal | OPTIONAL
vehicle_ledger | description | text | MANDATORY
vehicle_ledger | reference_id | integer | OPTIONAL
vehicle_ledger | reference_type | varchar | OPTIONAL
vehicle_ledger | created_at | timestamp | MANDATORY
financial_ledger
financial_ledger | id | bigint | MANDATORY | PRIMARY KEY, Auto-Increment
financial_ledger | partner_id | integer | OPTIONAL | FK → partners.id
financial_ledger | driver_id | integer | OPTIONAL | FK → drivers.id
financial_ledger | vehicle_id | integer | OPTIONAL | FK → vehicles.id
financial_ledger | workshop_id | integer | OPTIONAL | FK → workshops.id
financial_ledger | hisaab_master_id | integer | OPTIONAL | FK → hisaab_master.id
financial_ledger | driver_ledger_id | integer | OPTIONAL | FK → driver_ledger.id
financial_ledger | vehicle_ledger_id | integer | OPTIONAL | FK → vehicle_ledger.id
financial_ledger | maintenance_invoice_id | integer | OPTIONAL | FK → maintenance_invoices.id
financial_ledger | transaction_type | varchar | MANDATORY
financial_ledger | event_date | date | MANDATORY | Not Null
financial_ledger | amount | decimal | MANDATORY | Not Null
financial_ledger | tax_amount | decimal | OPTIONAL
financial_ledger | total_amount | decimal | MANDATORY
financial_ledger | remittance_towards | varchar | OPTIONAL
financial_ledger | utr_number | varchar | OPTIONAL
financial_ledger | status | varchar | MANDATORY | Default: 'Pending'
financial_ledger | file_url | varchar | OPTIONAL
financial_ledger | created_at | timestamp | MANDATORY
financial_ledger | modified_at | timestamp | OPTIONAL

## Hisaab and Financial
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated/QC | Blockers / Comments
hisaab_master
hisaab_master | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
hisaab_master | city_id | integer | MANDATORY | FK → cities.id
hisaab_master | week_number | integer | MANDATORY | Not Null
hisaab_master | start_date | date | MANDATORY
hisaab_master | end_date | date | MANDATORY
hisaab_master | status | varchar | MANDATORY
hisaab_master | created_at | timestamp | MANDATORY
hisaab_master | modified_at | timestamp | OPTIONAL
hisaab
hisaab | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
hisaab | hisaab_master_id | integer | MANDATORY | Not Null; FK → hisaab_master.id
hisaab | hisaab_type | varchar | MANDATORY
hisaab | driver_id | integer | OPTIONAL | FK → drivers.id
hisaab | vehicle_id | integer | OPTIONAL | FK → vehicles.id
hisaab | partner_id | integer | OPTIONAL | FK → partners.id
hisaab | active_days | integer | OPTIONAL
hisaab | onroad_days | integer | OPTIONAL
hisaab | daily_revenue_share | decimal | OPTIONAL
hisaab | net_weekly_revenue_share_calc | decimal | OPTIONAL
hisaab | ola_trips | integer | OPTIONAL
hisaab | ola_net_revenue | decimal | OPTIONAL
hisaab | ola_adjustment | decimal | OPTIONAL
hisaab | ola_ev_exemption | decimal | OPTIONAL
hisaab | ola_online_payment | decimal | OPTIONAL
hisaab | ola_incentive | decimal | OPTIONAL
hisaab | ola_week_os | decimal | OPTIONAL
hisaab | uber_trips | integer | OPTIONAL
hisaab | uber_total_revenue | decimal | OPTIONAL
hisaab | uber_cash_collection | decimal | OPTIONAL
hisaab | uber_toll | decimal | OPTIONAL
hisaab | uber_incentive | decimal | OPTIONAL
hisaab | uber_driver_subscription_charge | decimal | OPTIONAL
hisaab | uber_week_os | decimal | OPTIONAL
hisaab | vehicle_level_adjustment | decimal | OPTIONAL
hisaab | total_adjustments_calc | decimal | OPTIONAL
hisaab | challan | decimal | OPTIONAL
hisaab | tds | decimal | OPTIONAL
hisaab | accident | decimal | OPTIONAL
hisaab | dead_km_penalty | decimal | OPTIONAL
hisaab | current_week_os_calc | decimal | OPTIONAL
hisaab | pending_due | decimal | OPTIONAL
hisaab | total_os_calc | decimal | OPTIONAL
hisaab | to_collect_from_driver_calc | decimal | OPTIONAL
hisaab | to_pay_for_driver_calc | decimal | OPTIONAL
hisaab | letzryd_earning_calc | decimal | OPTIONAL
hisaab | letzryd_earning_per_day_calc | decimal | OPTIONAL
hisaab | actual_per_day_earning_calc | decimal | OPTIONAL
hisaab | ola_km | decimal | OPTIONAL
hisaab | uber_km | decimal | OPTIONAL
hisaab | ola_uber_total_km_calc | decimal | OPTIONAL
hisaab | total_gps_km | decimal | OPTIONAL
hisaab | ideal_gps_km | decimal | OPTIONAL
hisaab | dead_mile_calc | decimal | OPTIONAL
hisaab | dead_mile_pct_calc | decimal | OPTIONAL
hisaab | recomputation_policy | varchar | OPTIONAL
hisaab | status | varchar | MANDATORY | Default: 'Draft'
hisaab | created_at | timestamp | MANDATORY
hisaab | modified_at | timestamp | OPTIONAL

## Analytics and Views
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated/QC | Blockers / Comments
daily_driver_ledger
daily_driver_ledger | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
daily_driver_ledger | driver_id | integer | MANDATORY | Not Null; FK → drivers.id
daily_driver_ledger | vehicle_id | integer | OPTIONAL | FK → vehicles.id
daily_driver_ledger | event_timestamp | timestamp | MANDATORY | Not Null
daily_driver_ledger | attendance_status | varchar | MANDATORY
daily_driver_ledger | active_hours | decimal | OPTIONAL
daily_driver_ledger | total_trips | integer | OPTIONAL
daily_driver_ledger | total_earnings | decimal | OPTIONAL
daily_driver_ledger | incentives_earned | decimal | OPTIONAL
daily_driver_ledger | platform_fees | decimal | OPTIONAL
daily_driver_ledger | tds_deducted | decimal | OPTIONAL
daily_driver_ledger | cash_collected | decimal | OPTIONAL
daily_driver_ledger | rent_deduction | decimal | OPTIONAL
daily_driver_ledger | penalty_amount | decimal | OPTIONAL
daily_driver_ledger | net_payout | decimal | OPTIONAL
daily_driver_ledger | created_at | timestamp | MANDATORY
daily_driver_ledger | modified_at | timestamp | OPTIONAL
challan_driver_view
challan_driver_view | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
challan_driver_view | challan_log_id | integer | MANDATORY | Not Null; FK → challan_logs.id
challan_driver_view | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
challan_driver_view | driver_id | integer | OPTIONAL | FK → drivers.id
challan_driver_view | assignment_id | integer | OPTIONAL | FK → vehicle_assignments.id
challan_driver_view | challan_date | timestamp | MANDATORY
challan_driver_view | resolution_method | varchar | MANDATORY
challan_driver_view | created_at | timestamp | MANDATORY
daily_vehicle_ledger
daily_vehicle_ledger | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
daily_vehicle_ledger | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
daily_vehicle_ledger | event_date | date | MANDATORY | Not Null
daily_vehicle_ledger | total_kms_gps | decimal | OPTIONAL
daily_vehicle_ledger | trip_kms_total | decimal | OPTIONAL
daily_vehicle_ledger | dead_kms | decimal | OPTIONAL
daily_vehicle_ledger | utilization_rate_pct | decimal | OPTIONAL
daily_vehicle_ledger | total_trips | integer | OPTIONAL
daily_vehicle_ledger | total_revenue | decimal | OPTIONAL
daily_vehicle_ledger | toll_amount | decimal | OPTIONAL
daily_vehicle_ledger | maintenance_cost | decimal | OPTIONAL
daily_vehicle_ledger | challan_amount | decimal | OPTIONAL
daily_vehicle_ledger | is_in_workshop | boolean | OPTIONAL | Default: false
daily_vehicle_ledger | daily_pnl | decimal | OPTIONAL
daily_vehicle_ledger | created_at | timestamp | MANDATORY
daily_vehicle_ledger | modified_at | timestamp | OPTIONAL
daily_partner_ledger
daily_partner_ledger | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
daily_partner_ledger | partner_id | integer | MANDATORY | Not Null; FK → partners.id
daily_partner_ledger | event_date | date | MANDATORY | Not Null
daily_partner_ledger | active_vehicles | integer | OPTIONAL
daily_partner_ledger | total_revenue | decimal | OPTIONAL
daily_partner_ledger | revenue_share_deduction | decimal | OPTIONAL
daily_partner_ledger | net_revenue | decimal | OPTIONAL
daily_partner_ledger | total_expenses | decimal | OPTIONAL
daily_partner_ledger | total_challans | decimal | OPTIONAL
daily_partner_ledger | adjustments | decimal | OPTIONAL
daily_partner_ledger | daily_balance | decimal | OPTIONAL
daily_partner_ledger | created_at | timestamp | MANDATORY
daily_partner_ledger | modified_at | timestamp | OPTIONAL
fleet_performance_daily
fleet_performance_daily | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
fleet_performance_daily | event_date | date | MANDATORY | Not Null
fleet_performance_daily | city_id | integer | MANDATORY | FK → cities.id
fleet_performance_daily | total_vehicles | integer | OPTIONAL
fleet_performance_daily | active_vehicles | integer | OPTIONAL
fleet_performance_daily | in_maintenance_vehicles | integer | OPTIONAL
fleet_performance_daily | rfd_vehicles | integer | OPTIONAL
fleet_performance_daily | total_trips | integer | OPTIONAL
fleet_performance_daily | total_revenue | decimal | OPTIONAL
fleet_performance_daily | utilization_rate | decimal | OPTIONAL
fleet_performance_daily | created_at | timestamp | MANDATORY
fleet_performance_daily | modified_at | timestamp | OPTIONAL
maintenance_summary
maintenance_summary | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
maintenance_summary | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
maintenance_summary | period_start | date | MANDATORY | Not Null
maintenance_summary | year | integer | MANDATORY
maintenance_summary | repair_frequency | integer | OPTIONAL
maintenance_summary | downtime_days | integer | OPTIONAL
maintenance_summary | total_maintenance_cost | decimal | OPTIONAL
maintenance_summary | workshop_performance_score | decimal | OPTIONAL
maintenance_summary | created_at | timestamp | MANDATORY
maintenance_summary | modified_at | timestamp | OPTIONAL
daily_rental_log
daily_rental_log | id | integer | MANDATORY | PRIMARY KEY, Auto-Increment
daily_rental_log | date | date | MANDATORY | Not Null
daily_rental_log | vehicle_id | integer | MANDATORY | Not Null; FK → vehicles.id
daily_rental_log | driver_id | integer | OPTIONAL | FK → drivers.id
daily_rental_log | base_rent_amount | decimal | MANDATORY
daily_rental_log | vehicle_age_discount | decimal | OPTIONAL | Default: 0
daily_rental_log | custom_vehicle_discount | decimal | OPTIONAL | Default: 0
daily_rental_log | custom_driver_discount | decimal | OPTIONAL | Default: 0
daily_rental_log | final_rent_charged | decimal | MANDATORY
daily_rental_log | hisaab_id | integer | OPTIONAL | FK → hisaab.id
daily_rental_log | created_at | timestamp | MANDATORY

## Additional - Optional
Table Name | Column Name | Data Type | Mandatory / Optional | Constraints | Source | Data Populated/QC | Blockers / Comments